## Legend
Items Closed At The Last Review
Items Addressed Since The Last Review; May Be Closed If Approved
Item Removed
Items Currently Open

## NetCDF4_Reformatter
NetCDF4 Reformatting Toolkit: BUFR and GRIB Tailoring
CLI # | Check List Item (CLI) | Disposition |  |  |  |  | Risk | Action (Y/N) | Comments
|  | Pass | Conditional Pass | Defer | Waive | N/A
1 | PDR | X
2 | CDR | X
3 | TRR | X
4 | ARR

## ARR
Review Item | Originator | Review Item | Suggestions | Assigned To | Actions/Resolution | Risk Assesment | Risk Likelihood | Status | Closure Date

## TRR
Review Item | Originator | Review Item | Suggestions | Assigned To | Actions/Resolution | Risk Assesment | Risk Likelihood | Status | Closure Date
22 | Tom Schott | NDE needs to modify their contract to support completion of the SPSRB documents delivered by the NDE product teams. This is needed for a timely and smooth transition to OSPO. This is a project-level risk because there is concern over whether this can be done before NDE system is declared operational. | NDE may have to deliver the system to operations without the completed documentation. SPSRB may or may not find this acceptable. | Goodrum | Geof Goodrum is working to modify the NDE contract to include this documentation. | Low | Moderate | Open | Apr. 2013
23 | Tom Schott | CPC may have a need for JPSS NDVI in GRIB2 or netCDF4. | Contact Pingping Xie at CPC to see if they have a need for this product in either of these formats. | King | Tom King contacted Pingping Xie (Tom Schott was cc'd on the message). Pingping could not identify a user who needs this product in either of the formats. | Low | Moderate | Closed
24 | Tom Schott | There is still some concern about whether the "obviously" cloudy approach suggest by Andrew Collard has been approved by the EMC government management. This is not a problem for us to implement because, the scheme proposed by Andrew, is just a few lines of code. | Ask NCEP management (Derber and Grumbine) if this method is acceptable. Bring this up at the next NDE/EMC meeting. | King | John Derber and Robert Grumbine were aware of the solution and initially approved it. However, Robert Grumbine then became concerned that this method would exclude observations over frozen lakes at lower latitudes. After much discussion I suggested that we not thin since employing this method would add complexity to the BUFR code, slow it down, and would reduce the overall effectiveness of the thinning. In addition, this would reduce NCEP's flexibility in the event that they wish to use the data in these thinned areas for other reasons. After bringing this up NCEP agreed that dropping the thinning was acceptable (see email from Andrew on 11/9 - Bob and John were cc'd as well). | Low | Low | Closed
25 | Tom Schott | Tom Shott brought up the issue that NCEP may want the VIIRS Day/Night Band in BUFR. This is not a problem for us since we already have created and demonstrated the capability of producing this BUFR file. | Ask NCEP management (Derber) if VIIRS DNB BUFR is needed and, if so, when does it need to be made available? | King | This was issue was brought up to John Derber at the NDE/NCEP meeting. John had apparently already asked about it earlier. He said that he and no one else at this time needs the VIIRS DNB in BUFR and does not foresee a need in the future. | Low | Low | Closed

## CDR
Review Item | Originator | Review Item | Suggestions | Assigned To | Actions/Resolution | Risk Assesment | Risk Likelihood | Status | Closure Date
14 | Emily Graham | A naming convention between STAR and NDE CM baselines would need to be established for delivered DAPs. | STAR and NDE CM personnel should collaborate and have meetings to dicuss formats, definining fields, the process for delivering DAP with an official naming convention. Would recommend having a meeting before DAP is delivered. NDE CM would like to document naming convention for delivered DAPs in the NDE CM plan. | King | Since CDR, NDE has defined a naming convention for delivered DAPs. We recommend closing this. | Low | Low | Closed
15 | Geof Goodrum | Need to identify independent code review. | Document plan for an independent code review. Understand NESDIS QA process is being defined. | King | Such a code review is not part of the NESDIS QA, but code reviews are being implemented as part of the STAR EPL process. The problem with a purely independent code review is how to fund the time of outside reviewers to work on a task to which they are not assigned. The STAR EPL process will make code available to OSPO. If we agree that OSPO can adequately assist in the review process, this can be closed. | Low | Low | Closed
16 | Greg Krasowski | My contacts at EMC (Dennis Keyser and John Derber) are wondering if the addtion of netCDF4 conversion before BUFR conversion will add significant time to delivery of products. | They hope the delay in delivery time will be in terms of seconds, not minutes. | NDE | The toolkit, not NDE, will handle this conversion using the h5augjpss tool. The TRR tests demonstrate that this conversion is extremely fast (on the order of a second for each granule file). This risk can be closed. | Low | Low | Closed
17 | Jim Yoe | Encourage NWS (EMC, AWIPS) personnel to take part in future reviews, major meetings, as well as working level meetings. Notice that JCSDA and EMC were lightly represented in the CDR. | May need to establish a working group that facilitates consistent baselining of DAP configuration between STAR and NDE for all product systems. | NDE/Tom Schott/King | This risk here is that the needs of users (NDE and NWP) will not be adequately captured during the development process. NDE and NWP are included on the invitation to attend these reviews. There are regular pIPT meetings to help NDE connect with STAR product teams. In the last year, monthly STAR/NDE/EMC/JSCDA meetings have been initiated to coordinate the work of development teams with the needs of users. | Low | Low | Closed
18 | Donna McNamara | Will ESPC have BUFR expertise to provide maintenance for this toolkit? | Traditionally each product group in ESPC was responsible for BUFR. Using toolkit saves development costs, but it may reduce BUFR expertise and ownership in NDE and eventually ESPC. Not sure how to resolve this issue. | ESPC | This is not a risk for this project. ESPC will not be required to maintain this software. STAR will continue to maintain and upgrade it as new tailoring is needed. | NA | NA | Closed
19 | Larry Flynn | Should OMPS NP and TC be in the same BUFR file? | Flexibility of of FOV for OMPS NP pose a problem for converter if combined. | King/Song | They will be in separate output files. | Low | Low | Closed
20 | King | Solution proposed by NDE for tailoring ATMS and VIIRS into netCDF4 would require rewriting of readers to handle variable name changes and file bundling that would combine all VIIRS channels. | 3 options exist and have been tested: (1) Use the h5augjpss conversion tool from the program office to make the JPSS HDF5 readable by the netCDF4 library API functions, (2) Read the HDF5 files directly into the BUFR converter, (3) Use our own netCDF4 to HDF5 converter code. | King/Song | The Toolkit developers have chosen option 1 since this tool is maintained by funds from the JPSS program office to the HDF Group. | Low | High | Closed
21 | King | Processing all channels from VIIRS SDR would require too much CPU time on NDE production machine. | NWP would experience large latency for VIIRS SDR BUFR files or possibly the NDE hardware would not be able to keep up. | King/Song, Schott/NDE/NCEP/EMC | Meetings involving Tom Schott, NDE, and the STAR development team have, for now, reduced the requirement to 1 Imager and 4 Moderate resolutionchannels. The mitigation has reduced the likelihood of problems in the near term. For nominal data flow, just this VIIRS SDR BUFR conversion alone will need about 6 CPUs on NDE’s production machine to maintain the data flow. Full system tests of NDE running all product systems on nominal data flow will be the real test. | High | Medium | Closed

## PDR
No. | Originator | Review Item | Suggestions | Assigned To | Actions/Resolution | Risk Assesment | Risk Likelihood | Status | Closure Date
1 | King | NPOESS product formats and content are still changing, especially for VIIRS | Work through the NPOESS Data Format Working Group to obtain information on format and algorithm updates. Monitor the latest copies of the NPOESS Common Data Format Control Books (CDFCB) for any updates. Maintain contact with customers to inform them of any upstream product changes. Make the code design flexible so that changes in the upstream products translate into the minimum amount code revision. | King, Goodrum | The formats are now frozen and the toolkit has been tested successfully with the P72 datasets. | Low | High | Closed
2 | King | The roles and responsibilities regarding who shall generate the set of required SPSRB documents for NDE has not yet been decided | This issue as well as decisions regarding the content of the SPSRB documents is being worked by Ken Jensen and STAR, NDE, OSD, and OSDPD personnel. Reformatting Toolkit developers intend to participate in these meetings and discussions. | McHugh | This has been resolved in a series of meetings with the Common Standards Working Group, NDE, and STAR. The documentation templates have been approved by the SPSRB. | Low | Moderate | Closed
3 | King | There are small variations in the types of platforms and the versions of the compilers | Reformatting Toolkit developers will work with NDE during system tests in the integration and production phase to ensure that those results match the results from the units. The BCR process (mentioned earlier) should help to resolve these issues early on in development. | King | The results of NDE system tests will be compared to those of our unit tests. | Low | Moderate | Closed | Jun. 4, 2012
4 | Geof Goodrum | Data format translation involves some unit conversion and possible reduction of precision (significant digits) | Document data manipulations in the NDE Delivered Algorithm Package (in place of ATBD) | King | Any manipulation of data will be identified in the DAP. | Low | Low | Closed
5 | Geof Goodrum | Requirement section: traceability to L1 requirements is a strength. This section mingles project requirements, system requirements and assumptions | Clearly identify assumptions up-front, including expectations of the NDE system. Remove "NDE shall…" requirements. NDE team will validate assumption and assume new requirements if necessary | King, Koval | The PDR and RAD have been revised to identify only the Tailoring project’s requirements. The language in the requirements analysis has been modified to express the project’s understanding of NDE’s roles. |  |  | Closed
6 | Walter Wolf | Risk on NDVI and snow mask. Test GRIB2 functionality before/for CDR. | RAD/Requirements meeting before CDR | Wolf | This has not yet been done. The GVF product will be in GRIB2. The functionality will be added to the toolkit in January 2012. By the time of the Phase 2 EDR TRR this capability will be present. | Moderate | Low | Open | ??
7 | Walter Wolf | Set up a meeting with Tom Schott on new aerosol product requirements/requests |  | Wolf | This has been done. |  |  | Closed
8 | Jim Yoe | Requirement to write tailoring into GRIB2 VIIRS snow cover and vegetation index. Need to insure that view point M. EK is known and understand by EMC director | Yoe/Schott to contact M. EK and coordinate w/s Lord/EMC/JCSDA before decisions (i.e. snow cover and vegetation index may decide differently) | Yoe, Schott | This has been done. | Moderate | Moderate | Closed
9 | Tom Schott | NWS and other NWP users will want ATMS/CrIS spectral response functions. They will also want OMPS key calibration functions. This information appear to be contained In ITAR document that we cannot share with foreign users | NDE should work with IPO to determine if we can receive and release that ATMS, CrIS and OMPS SPF and KCF data to foreign NWP users. It is our understanding that the information is in ITAR documentation | Yoe | This is not a risk to the Tailoring project. It is a user need that would be best addressed by the JPSS Program Office. | Moderate | High | Closed
10 | L. Flynn | Minor terminology and details. 1) IPs: Not all IPs are created equal. DIPs: Delivered IPs (OMPS NP O3 Profile). RIPS: Retained IPs 2) O3 POP is now Atmospheric Chemistry POP. 3) OMPS Total Ozone Algorithm is multiple triplet Not v8 primary. Output fields are equivalent to v8 on GOME-2 | 1) Not existence of DIPs. Current OMPS DIP is v6. 2) Change in POP list. 3) Get sample EDR compare fields to GOME-2 v8 PMF | King | The PDR has been updated to contain the enhanced IP definitions and ozone algorithm version. |  |  | Closed
11 | Sid Boukabara | Risk #1: a lot of efforts would be part on projects/NDE to convert to NetCDF4 (depend heavily on NDE schedule for the conversion to NetCDF4). | Make converter tool flexible to accept other formats not just NetCDF4. Those formats should include:1) project formats (MIRS, NUCAPS, Ozone etc.) 2) HDF5 format IDPs | King | We recommend closing this since it is not a risk to the Tailoring project. It’s a risk to NDE and the Product Teams. |  |  | Closed
12 | Sid Boukabara | Risk #2: Timelines gets tight If we have to convert HDF5, project format to NetCDF4 and then to other format | Asses timeliness issue (due to added conversion step) | King, NDE | The toolkit, not NDE, will handle this conversion using the h5augjpss tool. The TRR tests demonstrate that this conversion is extremely fast (on the order of a second for each granule file). This risk can be closed. | Moderate | Moderate | Closed
13 | Sid Boukabara | Good idea to have placeholder for additional quality flags (for land mask etc.). Filling them depends on timelines. Why not the same thing is done to ATMS BUFR table | Plan for placeholders of additional quality flags for ATMS radiance BUFR table. The need maybe there but not expressed | Song | There are already spare bit fields in the ATMS BUFR quality flag fields if new ATMS quality flags become available. With respect to the tailoring software, it’s not within the scope of this project to assess data quality such that we generate and add to the BUFR our own new quality information. |  |  | Closed